LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Hazelwood-1 | REPORT No. : | 2 | DFS: | 1 | DATE : | 25-03-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 483m | LAST DEPTH : | 293m(rkb) | 24 HR PROGRESS: | 190.00m | PTD : |  |
| TOTAL FUEL : | 12,800 lt | FUEL USAGE : | 2,200 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Drilled 400mm hole from 483m to 513m- Circulate and work drill string while repairing rotary chain |
| Next 24 Hrs Op | Drill to casing depth –circulate hole clean – run survey-wiper trip back to 280m-R.I.H-circ-trip out for 334mm casing-run same |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 1 |  |  | Drilling | 15.00 |  | Density | 1.068 | S.G. |
| Size (mm) | 400 |  |  | Tripping |  |  | Viscosity | 65 | Sec |
| Make | Smith |  |  | Surveys | 4.00 |  | Water Loss | 12.5 | Cc |
| Type | GX-1VC |  |  | Rigged up |  |  | pH | 10.5 | Strip |
| IADC Code |  |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | MM4714 |  |  | Circulate Sample |  |  | PV / YP | 16 / 20 | Cp/lb/100’ |
| Nozzles (32) | 18-22-22 |  |  | Casing |  |  | Gels | 5 / 8 | S/m |
| Depth in (m) | 293.00 |  |  | Cementing |  |  | Sand | tr | % Vol |
| Depth out (m) |  |  |  | Surveys |  |  | Solids | 3.9 | % Vol |
| Total Metres | 190 |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 15.00 |  |  | Rig Service/slip & cut |  |  | K+ |  | Mg/l |
| WOB (kg) | 2min-5max |  |  | Pick up BHA | 2.50 |  | Chlorides | 1,800 | Mg/l |
| RPM | 100 |  |  | Drill out Cmt | 2.50 |  | PHPA |  |  |
| Condition | Still in Hole |  |  | Breakdown kelly |  |  | KCL | % |  |
| Impact Force | 441 |  |  | Wait On Cement |  |  | Daily Cost $ | 4,893 |
| Jet Velocity | 176 |  |  | Test BOPs |  |  | Cum Cost $ | 4,893 |
| B.H.A.: | 400mm Bit-Bit Sub-2 x 8” Drill Collars- Stabilizer-Crossover sub- 8 x 6-1/4” Drill Collars- 4 x HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 8deg plus | ° at | 258 | m |  | Type | Amount |
| 0000 | 02:30 | Picked up pipe ran in hole tagged cement at 258m |  | 12 deg | ° at | 319 | m |  | Aus-Gel | 420 |
| 02:30 | 04:00 | Ran two surveys at 258m with 8 degree chart (max) |  | 11 deg | ° at | 357 | m |  | Dextrid |  |
| 04:00 | 06:30 | Drilled out cement from 258m to 293m |  | 9 deg | ° at | 414 | m |  | Pac - R |  |
| 06:30 | 09:30 | Drilled 400mm hole from 293m to 332m |  | 3 deg | ° at | 471 | m |  | Barite |  |
| 09:30 | 10:00 | Circulated hole clean |  |  | ° at |  | m |  | Bulk Barite |  |
| 10:00 | 10:30 | Ran survey at 319m used 16 deg chart |  |  | ° at |  | m |  | PHPA/ KCL |  |
| 10:30 | 13:30 | Drilled 400mm hole from 332m to 369m |  |  | ° at |  | m |  | Caustic Soda |  |
| 13:30 | 14:00 | Ran survey at 357m |  |  |  |  |
| 14:00 | 19:00 | Drilled 400mm hole from 369m to 426m |  | PUMP 1 |  | PUMP 2 |
| 19:00 | 19:30 | Ran survey at 414m |  | Liner | 108 | mm |  | Liner | 108 | mm |
| 19:30 | 23:30 | Drilled 400mm hole from 426m to 483m |  | Pressure | 4900 | kPa |  | Pressure | 4900 | KPa |
| 23:30 | 24:00 | Ran survey at 471m |  | A.V. DP | 18 | m/min |  | A.V. DP | 18 | m/min |
|  |  |  |  | A.V. DC | 20 | m/min |  | A.V. DC | 20 | m/min |
|  |  | Controlled the drilling parameters to correct the well |  | SPM | 130 |  | SPM | 130 |
|  |  | Deviation from bottom of conductor pipe ( 12 deg ) |  | LPM | 1,200 |  | LPM | 1,200 |
|  |  | at 293m |  |  |  |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 450 | mm |
|  |  |  |  | Class Bulk |  |  | Weight |  | Kg/m |
|  |  | Conductor pipe installed by Drilltec Cardwell HL Rig |  | % |  |  |  | Grade | Line pipe |  |
|  |  | Deviation at 286m is 12 degrees |  | % |  |  |  | Connection | Welded |  |
|  |  |  |  | % |  |  |  | Joints |  |  |
|  |  |  |  | % |  |  |  | Length | 281.00 | m |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 286.00 m from RKB | m |

,66