LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Hazelwood-1 | REPORT No. : | 2 | DFS: | 1 | DATE : | 25-03-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 483m | LAST DEPTH : | 293m(rkb) | 24 HR PROGRESS: | 190.00m | PTD : |  |
| TOTAL FUEL : | 12,800 lt | FUEL USAGE : | 2,200 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Drilled 400mm hole from 483m to 513m- Circulate and work drill string while repairing rotary chain |  |  |  |  |  |  |
| Next 24 Hrs Op | Drill to casing depth –circulate hole clean – run survey-wiper trip back to 280m-R.I.H-circ-trip out for 334mm casing-run same |  |  |  |  |  |  |
| Site Personnel: | Lou DeVattimo - Supervisor |  |  |  |  |  |  |

|  |  | BIT INFORMATION |  |  |  |  |  |  |  | # OPS BREAKDOWN |  |  |  |  |  |  |  |  |  | # MUD PROPERTIES |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Bit Number |  |  | 1 |  |  |  |  | Drilling |  |  |  |  | 15.00 |  |  |  |  | Density |  |  | 1.068 |  |  | S.G. |  |  |
|  |  | Size (mm) |  |  | 400 |  |  |  |  | Tripping |  |  |  |  |  |  |  |  |  | Viscosity |  |  | 65 |  |  | Sec |  |  |
|  |  | Make |  |  | Smith |  |  |  |  | Surveys |  |  |  |  | 4.00 |  |  |  |  | Water Loss |  |  | 12.5 |  |  | Cc |  |  |
|  |  | Type |  |  | GX-1VC |  |  |  |  | Rigged up |  |  |  |  |  |  |  |  |  | pH |  |  | 10.5 |  |  | Strip |  |  |
|  |  | IADC Code |  |  |  |  |  |  |  | Testing/tools |  |  |  |  |  |  |  |  |  | Filter Cake |  |  | 1 |  |  | 32 nd |  |  |
|  |  | Serial Number |  |  | MM4714 |  |  |  |  | Circulate Sample |  |  |  |  |  |  |  |  |  | PV / YP |  |  | 16 / 20 |  |  | Cp/lb/100’ |  |  |
|  |  | Nozzles (32) |  |  | 18-22-22 |  |  |  |  | Casing |  |  |  |  |  |  |  |  |  | Gels |  |  | 5 / 8 |  |  | S/m |  |  |
|  |  | Depth in (m) |  |  | 293.00 |  |  |  |  | Cementing |  |  |  |  |  |  |  |  |  | Sand |  |  | tr |  |  | % Vol |  |  |
|  |  | Depth out (m) |  |  |  |  |  |  |  | Surveys |  |  |  |  |  |  |  |  |  | Solids |  |  | 3.9 |  |  | % Vol |  |  |
|  |  | Total Metres |  |  | 190 |  |  |  |  | Circulate & Condition |  |  |  |  |  |  |  |  |  | Oil |  |  |  |  |  | % Vol |  |  |
|  |  | Hours |  |  | 15.00 |  |  |  |  | Rig Service/slip & cut |  |  |  |  |  |  |  |  |  | K+ |  |  |  |  |  | Mg/l |  |  |
|  |  | WOB (kg) |  |  | 2min-5max |  |  |  |  | Pick up BHA |  |  |  |  | 2.50 |  |  |  |  | Chlorides |  |  | 1,800 |  |  | Mg/l |  |  |
|  |  | RPM |  |  | 100 |  |  |  |  | Drill out Cmt |  |  |  |  | 2.50 |  |  |  |  | PHPA |  |  |  |  |  |  |  |  |
|  |  | Condition |  |  | Still in Hole |  |  |  |  | Breakdown kelly |  |  |  |  |  |  |  |  |  | KCL |  |  | % |  |  |  |  |  |
|  |  | Impact Force |  |  | 441 |  |  |  |  | Wait On Cement |  |  |  |  |  |  |  |  |  | Daily Cost $ |  |  | 4,893 |  |  |  |  |  |
|  |  | Jet Velocity |  |  | 176 |  |  |  |  | Test BOPs |  |  |  |  |  |  |  |  |  | Cum Cost $ |  |  | 4,893 |  |  |  |  |  |
|  |  | B.H.A.: |  | 400mm Bit-Bit Sub-2 x 8” Drill Collars- Stabilizer-Crossover sub- 8 x 6-1/4” Drill Collars- 4 x HWDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | HOURLY OPERATIONS SUMMARY (0000 – 2400) |  |  |  |  |  |  |  |  |  | # SURVEYS |  |  |  |  |  |  |  |  |  | # CHEMICALS USED |  |  |  |  |  |  |
|  |  | From | To |  |  | Operation |  |  |  |  |  | 8deg plus |  | ° at |  | 258 |  |  | m |  |  | Type |  |  | Amount |  |  |  |
|  |  | 0000 | 02:30 |  |  | Picked up pipe ran in hole tagged cement at 258m |  |  |  |  |  | 12 deg |  | ° at |  | 319 |  |  | m |  |  | Aus-Gel |  |  | 420 |  |  |  |
|  |  | 02:30 | 04:00 |  |  | Ran two surveys at 258m with 8 degree chart (max) |  |  |  |  |  | 11 deg |  | ° at |  | 357 |  |  | m |  |  | Dextrid |  |  |  |  |  |  |
|  |  | 04:00 | 06:30 |  |  | Drilled out cement from 258m to 293m |  |  |  |  |  | 9 deg |  | ° at |  | 414 |  |  | m |  |  | Pac - R |  |  |  |  |  |  |
|  |  | 06:30 | 09:30 |  |  | Drilled 400mm hole from 293m to 332m |  |  |  |  |  | 3 deg |  | ° at |  | 471 |  |  | m |  |  | Barite |  |  |  |  |  |  |
|  |  | 09:30 | 10:00 |  |  | Circulated hole clean |  |  |  |  |  |  |  | ° at |  |  |  |  | m |  |  | Bulk Barite |  |  |  |  |  |  |
|  |  | 10:00 | 10:30 |  |  | Ran survey at 319m used 16 deg chart |  |  |  |  |  |  |  | ° at |  |  |  |  | m |  |  | PHPA/ KCL |  |  |  |  |  |  |
|  |  | 10:30 | 13:30 |  |  | Drilled 400mm hole from 332m to 369m |  |  |  |  |  |  |  | ° at |  |  |  |  | m |  |  | Caustic Soda |  |  |  |  |  |  |
|  |  | 13:30 | 14:00 |  |  | Ran survey at 357m |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 14:00 | 19:00 |  |  | Drilled 400mm hole from 369m to 426m |  |  |  |  |  | # PUMP 1 |  |  |  |  |  |  |  |  |  | # PUMP 2 |  |  |  |  |  |  |
|  |  | 19:00 | 19:30 |  |  | Ran survey at 414m |  |  |  |  |  | Liner |  |  |  | 108 |  |  | mm |  |  | Liner |  |  | 108 |  | mm |  |
|  |  | 19:30 | 23:30 |  |  | Drilled 400mm hole from 426m to 483m |  |  |  |  |  | Pressure |  |  |  | 4900 |  |  | kPa |  |  | Pressure |  |  | 4900 |  | KPa |  |
|  |  | 23:30 | 24:00 |  |  | Ran survey at 471m |  |  |  |  |  | A.V. DP |  |  |  | 18 |  |  | m/min |  |  | A.V. DP |  |  | 18 |  | m/min |  |
|  |  |  |  |  |  |  |  |  |  |  |  | A.V. DC |  |  |  | 20 |  |  | m/min |  |  | A.V. DC |  |  | 20 |  | m/min |  |
|  |  |  |  |  |  | Controlled the drilling parameters to correct the well |  |  |  |  |  | SPM |  |  |  | 130 |  |  |  |  |  | SPM |  |  | 130 |  |  |  |
|  |  |  |  |  |  | Deviation from bottom of conductor pipe ( 12 deg ) |  |  |  |  |  | LPM |  |  |  | 1,200 |  |  |  |  |  | LPM |  |  | 1,200 |  |  |  |
|  |  |  |  |  |  | at 293m |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | # CEMENT DATA |  |  |  |  |  |  |  |  |  | # LAST CASING |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Sacks Halliburton |  |  |  |  |  |  |  |  |  | Size |  | 450 |  |  | mm |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Class Bulk |  |  |  |  |  |  |  |  |  | Weight |  |  |  |  | Kg/m |  |
|  |  |  |  |  |  | Conductor pipe installed by Drilltec Cardwell HL Rig |  |  |  |  |  | % |  |  |  |  |  |  |  |  |  | Grade |  | Line pipe |  |  |  |  |
|  |  |  |  |  |  | Deviation at 286m is 12 degrees |  |  |  |  |  | % |  |  |  |  |  |  |  |  |  | Connection |  | Welded |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | % |  |  |  |  |  |  |  |  |  | Joints |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | % |  |  |  |  |  |  |  |  |  | Length |  | 281.00 |  |  | m |  |
|  |  | Days since | LTA |  |  |  |  |  |  |  |  | Av. Wt |  |  |  |  |  |  |  |  |  | Shoe |  | 286.00 m from RKB |  |  | m |  |

,66