LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Hazelwood-1 | REPORT No. : | 6 | DFS: | 5 | DATE : | 29-03-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 556m | LAST DEPTH : | 556 | 24 HR PROGRESS: | 0 | PTD : | 2,700m |
| TOTAL FUEL : | 25,300 | FUEL USAGE : | 1,300 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Finished to wash and light reamed hole to bottom at 556m |
| Next 24 Hrs Op | Drill 31mm hole with Bit # 2 from 556m |
|  | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 1 | 2 |  | Drilling |  |  | Density | 1.092 | S.G. |
| Size (mm) | 400 | 311 |  | Tripping |  |  | Viscosity | 60 | Sec |
| Make | Smith | Reed |  | Surveys |  |  | Water Loss | 14.00 | Cc |
| Type | GX-1VC | DSX-140A |  | Rigged up |  |  | pH | 10.0 | Strip |
| IADC Code | 2-1-7 | S 323 |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | MM4714 | 206579 |  | Circulate Sample |  |  | PV / YP | 8 / 26 | Cp/lb/100’ |
| Nozzles (32) | 18-22-22 | 14-14-14-14-14-14-14 |  | Casing |  |  | Gels | 5 / 7 | S/m |
| Depth in (m) | 293.00 | 556 |  | Cementing |  |  | Sand | tr | % Vol |
| Depth out (m) | 556 |  |  | Test BOP | 5.50 |  | Solids | 5.4 | % Vol |
| Total Metres | 263 |  |  | Circulate & Condition | 1.00 |  | Oil |  | % Vol |
| Hours | 30.00 |  |  | Rig Service |  |  | K+ |  | Mg/l |
| WOB (kg) | 5min-12max |  |  | Pick up BHA | 5.50 |  | Chlorides | 900 | Mg/l |
| RPM | 100 |  |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | T-2 B-2 In gauge |  |  | Repair rig |  |  | KCL | % |  |
| Impact Force | 461 |  |  | Wait On Cement |  |  | Daily Cost $ | Nil |
| Jet Velocity | 176 |  |  | Rig up BOPs | 12.00 |  | Cum Cost $ | 6,390 |
| B.H.A.: | 311mm PDC bit-near bit stab-2 x 8” drill collars-stabilizer-crossover sub-non magnetic drill collar-8 x 6-1/4 inch drill collars-drilling jar-2 x 6-1/4” drill |
|  | Collars-4 x hevi-wate drill pipe total length 168.60m wt below jars 40,000lbs |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 8deg plus | ° at | 258 | m |  | Type | Amount |
| 0000 | 03:00 | Continued to make up BOP |  | 12 deg | ° at | 319 | m |  | Aus-Gel |  |
| 03:00 | 07:00 | Installed flo-line and choke manifold lines |  | 11 deg | ° at | 357 | m |  | Dextrid |  |
| 07:00 | 09:30 | Removed the BOP skid and connected Koomey lines |  | 9 deg | ° at | 414 | m |  | Pac - R |  |
| 09:30 | 10:00 | Function tested all lines |  | 3 deg | ° at | 471 | m |  | Barite |  |
| 10:00 | 12:00 | Rigged up for BOP test |  | 2 deg | ° at | 546 | m |  | Bulk Barite |  |
| 12:00 | 13;00 | Pressure tested Blind Rams against Casing to 1500psi |  |  | ° at |  | m |  | PHPA/ KCL |  |
| 13:00 | 18:00 | Made up 311mm drilling assembly tripped in to 356m |  |  | ° at |  | m |  | Caustic Soda |  |
| 18:00 | 19;00 | Layed out 20 joints of drill pipe |  |  |  |  |
| 19:00 | 20:00 | Ran pipe from derrick to 394m |  | PUMP 1 |  | PUMP 2 |
| 20:00 | 21:00 | Picked up Kelly washed to top of float collar |  | Liner | 108 | mm |  | Liner | 108 | mm |
| 21:00 | 21:30 | Rest the AOI instrument unit |  | Pressure |  | kPa |  | Pressure |  | KPa |
| 21:30 | 24:00 | Pressure tested the Bop and choke manifold |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM |  |  | SPM |  |
|  |  |  |  | LPM |  |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 340 | mm |
|  |  |  |  | Class Bulk |  |  | Weight | 81 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | Buttress |  |
|  |  |  |  | % |  |  |  | Joints | 38 |  |
|  |  |  |  | % |  |  |  | Length | 420.00 m RKB |  |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 420.0 m from RKB | m |

,66