LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Hazelwood-1 | REPORT No. : | 8 | DFS: | 7 | DATE : | 31-03-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 765m | LAST DEPTH : | 669 | 24 HR PROGRESS: | 96 | PTD : | 2,700m |
| TOTAL FUEL : | 17,600 | FUEL USAGE : | 4,400 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Drilled 311mm hole from 763m to 787m |
| Next 24 Hrs Op | Drill ahead |
|  | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 1 | 2 |  | Drilling | 19.00 |  | Density | 1.068 | S.G. |
| Size (mm) | 400 | 311 |  | Tripping | 3.00 |  | Viscosity | 35 | Sec |
| Make | Smith | Reed |  | Surveys | 0.50 |  | Water Loss | 13.00 | Cc |
| Type | GX-1VC | DSX-140A |  | Rigged up |  |  | pH | 10.0 | Strip |
| IADC Code | 2-1-7 | S 323 |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | MM4714 | 206579 |  | Circulate Sample |  |  | PV / YP | 7 / 3 | Cp/lb/100’ |
| Nozzles (32) | 18-22-22 | 14-14-14-14-14-14-14 |  | Casing |  |  | Gels | 1/ 2 | S/m |
| Depth in (m) | 293.00 | 556 |  | Cementing |  |  | Sand | tr | % Vol |
| Depth out (m) | 556 |  |  | Test BOP |  |  | Solids | 3.9 | % Vol |
| Total Metres | 263 | 209 |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 30.00 | 17 |  | Rig Service | 1.00 |  | K+ |  | Mg/l |
| WOB (kg) | 5min-12max | 5 to 10 |  | Pick up BHA |  |  | Chlorides | 3,000 | Mg/l |
| RPM | 100 | 90-100 |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | T-2 B-2 In gauge | In hole |  | Repair rig |  |  | KCL | % |  |
| Impact Force | 461 | 610 |  | Wait On Cement |  |  | Daily Cost $ | 524 |
| Jet Velocity | 176 | 253 |  | Slipped block line | 0.50 |  | Cum Cost $ | 14,147 |
| B.H.A.: | 311mm PDC bit-near bit stab-2 x 8” drill collars-stabilizer-crossover sub-non magnetic drill collar-8 x 6-1/4 inch drill collars-drilling jar-2 x 6-1/4” drill |
|  | Collars-4 x hevi-wate drill pipe total length 168.60m wt below jars 40,000lbs |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 8deg plus | ° at | 258 | m |  | Type | Amount |
| 0000 | 16:00 | Drilled 311mm hole from 669m to 754m |  | 12 deg | ° at | 319 | m |  | Amc Pac L |  |
| 16:00 | 16:30 | Circulated and ran survey at 742m |  | 11 deg | ° at | 357 | m |  | Amc Pac R | 1 |
| 16:30 | 17:30 | Adjusted the mast to hang blocks at well center |  | 9 deg | ° at | 414 | m |  | Potassium Chloride |  |
| 17:30 | 19:00 | Wiper tripped back to shoe at 420m hole good |  | 3 deg | ° at | 471 | m |  | Barite | 34 |
| 19:00 | 19:30 | Slipped 52 ft of Block line |  | 2 deg | ° at | 546 | m |  | Bulk Barite |  |
| 19;30 | 21:00 | Tripped back in hole from 420m to bottom at 754m |  | 2deg 25dN | ° at | 581 | m |  | PHPA |  |
| 21:00 | 24;00 | Drilled 311mm hole from 754m to 765m |  | 1.5 | ° at | 742 | m |  | Caustic Soda |  |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  | Wiper trip indicated hole condition good with no |  | Liner | 108 | mm |  | Liner | 108 | mm |
|  |  | excessive over pull deviation drag only |  | Pressure | 6,300 | kPa |  | Pressure | 6,300 | KPa |
|  |  |  |  | A.V. DP | 111 | f/min |  | A.V. DP | 111 | f/min |
|  |  |  |  | A.V. DC | 167 | fmin |  | A.V. DC | 167 | f/min |
|  |  |  |  | SPM | 140 |  | SPM | 140 |
|  |  |  |  | GPM | 293 |  | GPM | 293 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 340 | mm |
|  |  |  |  | Class Bulk |  |  | Weight | 81 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | Buttress |  |
|  |  |  |  | % |  |  |  | Joints | 38 |  |
|  |  |  |  | % |  |  |  | Length | 420.00 m RKB |  |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 420.0 m from RKB | m |

,66