| PETRO TECH PTY LTD A.B.N. 009 116 429 | Registered Office: Level 11, 500 Collins Street, Melbourne, Vic. 3000 Phone: (03) 9629 1566 | Postal Address PO Box 300, Collins Street West Melbourne Vic. 8007 Fax: (03) 9629 1624 |
| --- | --- | --- |

# Hazelwood-1 (Stage 2) Wellsite

# via Morwell

April 4th 2007

# Hazelwood-1 (stage two) Drilling Report #11 – April 4th 2007

Well History

Site works commenced on the 22nd January with the levelling of the pad, the placing of the gravel and the excavating of the sumps and flare pit. The first stage of drilling at Hazelwood-1 commenced on Friday 23rd February with the Drilltec Cardwell HL rig drilling the surface hole to a depth of 288m before running the 450mm (18”) surface casing to 281m. The Drilltec rig was moved off site and the Century#11 rig commenced mobilising to the site and rigging up on Monday 19th March with the drilling of stage 2 commencing at 6pm on Saturday 24th March.

24 Hour Progress

At 6am this morning the contractor was picking up the 311mm (12-1/4”) insert drill bit and preparing to run back into the hole to attempt to drill ahead in the very hard rock which was encountered at 1068m. The hole was drilled to a depth of 1072m, having progressed 84m in the past 24hrs, before it was decided to pull the PDC bit due to slow drill rate. The rock below 1068m appears to be a very hard, siliceous sandstone but is difficult to determine due to the poor sample quality caused by the slow drilling rate and the abundance of cavings contaminating the sample. The mud was conditioned, increasing viscosity and weight, prior to pulling the bit to ensure hole stability during the changing of the bit. The Strzelecki Formation above 1068m showed very little change from previous reports.

Next 24 Hours

Continue to pick up the insert bit and run it into the hole and drill ahead in 311mm (12-1/4”) hole towards the revised casing point at approximately 1300m.

Safety and Environment

No safety or environmental incidents have occurred in the past 24hrs.

Tim O’Brien

Operations Manager

Lakes Oil N.L. as operator for Petro Tech Pty Ltd