| PETRO TECH PTY LTD A.B.N. 009 116 429 | Registered Office: Level 11, 500 Collins Street, Melbourne, Vic. 3000 Phone: (03) 9629 1566 | Postal Address PO Box 300, Collins Street West Melbourne Vic. 8007 Fax: (03) 9629 1624 |
| --- | --- | --- |

# Hazelwood-1 (Stage 2) Wellsite

# via Morwell

March 27th 2007

# Hazelwood-1 (stage two) Drilling Report #3 – March 27th 2007

Well History

Site works commenced on the 22nd January with the levelling of the pad, the placing of the gravel and the excavating of the sumps and flare pit. The first stage of drilling at Hazelwood-1 commenced on Friday 23rd February with the Drilltec Cardwell HL rig drilling the surface hole to a depth of 288m before running the 450mm (18”) surface casing to 281m. The Drilltec rig was moved off site and the Century#11 rig commenced mobilising to the site and rigging up on Monday 19th March with the drilling of stage 2 commencing at 6pm on Saturday 24th March.

24 Hour Progress

At 6am this morning the contractor was rigging up to run the 13-3/8” casing. The 16” hole was drilled to a depth of 556m, having drilled 43m in the past 24hrs before it was decided to pull the bit and run the casing due to a very slow penetration rate of less then 1m/hr. The top of the Strzelecki Formation was encountered at a depth of 545m underlying weathered volcanics. A survey was taken at the bottom of the hole indicating the deviation of the hole had dropped back to 2º and the wiper trip conducted back to the 18” casing show indicated the hole is in good condition. The rig was shut down for repairs to a broken rotary chain for 4.5hrs before drilling recommenced yesterday morning.

Next 24 Hours

Continue to run the 13-3/8” casing to 550m before cementing the same in place. After waiting on the cement to set the 13-5/8” wellhead and BOP will be installed and pressure tested prior to drilling out the 13-3/8” casing shoe and drilling ahead in 12-1/4” hole to the next casing point at approximately 1400m.

Safety and Environment

An incident report was submitted for a twisted ankle incurred by the electrician when stepping off the cable box onto the pad. No environmental incidents have occurred.

Tim O’Brien

Operations Manager

Lakes Oil N.L. as operator for Petro Tech Pty Ltd