| PETRO TECH PTY LTD A.B.N. 009 116 429 | Registered Office: Level 11, 500 Collins Street, Melbourne, Vic. 3000 Phone: (03) 9629 1566 | Postal Address PO Box 300, Collins Street West Melbourne Vic. 8007 Fax: (03) 9629 1624 |
| --- | --- | --- |

# Hazelwood-1 (Stage 2) Wellsite

# via Morwell

April 8th 2007

# Hazelwood-1 (stage two) Drilling Report #15 – April 8th 2007

Well History

Site works commenced on the 22nd January with the levelling of the pad, the placing of the gravel and the excavating of the sumps and flare pit. The first stage of drilling at Hazelwood-1 commenced on Friday 23rd February with the Drilltec Cardwell HL rig drilling the surface hole to a depth of 288m before running the 450mm (18”) surface casing to 281m. The Drilltec rig was moved off site and the Century#11 rig commenced mobilising to the site and rigging up on Monday 19th March with the drilling of stage 2 commencing at 6pm on Saturday 24th March.

24 Hour Progress

At 6am this morning the contractor was laying out the 8” drill collars prior to rigging up to run the 9-5/8” casing. The hole was drilled to a depth of 1298m where it was decided to run casing. A survey was taken indicating the hole had deviated out 15º due to the hard drilling and the dip of the Strzelecki Formation. A wiper trip was then run back to the 13-3/8” casing shoe, which indicated that the hole was in good condition. Another survey was run once back on bottom following the wiper trip to confirm the high reading on the previous survey but it was a misrun. A survey will be run following the running of the casing to confirm the reading. The Strzelecki Formation appeared to have a higher sand content towards the bottom of the hole and the drilling rate increased as a result of this.

Next 24 Hours

Continue to layout the 8” collars and 12-1/4” stabilisers and rig up and run the 9-5/8” casing and cement it in place.

Safety and Environment

No safety or environmental incidents have occurred in the past 24hrs.

Tim O’Brien

Operations Manager

Lakes Oil N.L. as operator for Petro Tech Pty Ltd