| PETRO TECH PTY LTD A.B.N. 009 116 429 | Registered Office: Level 11, 500 Collins Street, Melbourne, Vic. 3000 Phone: (03) 9629 1566 | Postal Address PO Box 300, Collins Street West Melbourne Vic. 8007 Fax: (03) 9629 1624 |
| --- | --- | --- |

- Hazelwood-1 (Stage 2) Wellsite

- via Morwell

April 13th 2007

- Hazelwood-1 (stage two) Drilling Report #20 – April 13th 2007

Well History

Site works commenced on the 22nd January with the levelling of the pad, the placing of the gravel and the excavating of the sumps and flare pit. The first stage of drilling at Hazelwood-1 commenced on Friday 23rd February with the Drilltec Cardwell HL rig drilling the surface hole to a depth of 288m before running the 450mm (18”) surface casing to 281m. The Drilltec rig was moved off site and the Century#11 rig commenced mobilising to the site and rigging up on Monday 19th March with the drilling of stage 2 commencing at 6pm on Saturday 24th March.

24 Hour Progress

At 6am this morning the contractor was drilling ahead in 8-1/2” hole at a depth of 1431m having progressed 78m in the past 24hrs since the new BHA was run into the hole. The BHA was pulled from the hole to change around the stabilisers to try and get the hole to straighten up. On running back into the hole it was decided to change the BHA again so the BHA was stopped being run into the hole and pulled back to the surface where it was changed to two stabilisers at 30’ and 60’ on the recommendation of a directional driller. The BHA was run back into the hole and drilling recommenced. Good rate of penetration (5-15m/hr) has been maintained with little weight required on bit. The geology has become slightly more carbonaceous in the sands with a slight increase in background gas levels (up to 0.6units C1 94% C2 6%).

Next 24 Hours

Continue to drill ahead in 8-1/2” hole towards TD. A survey will be run at 1440m to see whether the deviation of the hole is improving or not with the new BHA.

Safety and Environment

No safety or environmental incidents have occurred in the past 24hrs.

Tim O’Brien

Operations Manager

Lakes Oil N.L. as operator for Petro Tech Pty Ltd