DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 12, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 237 | 363 |
| --- | --- | --- |
| CAMERON | 1688 | 1688 |
| HALLIBURTON | 3475 | 3475 |
| SCHLUMBERGER | 2417 | 2417 |
| ISDL | 237 | 647 |
| ISS | 225 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 12, 2007

Supervisor:	Davis, Brian

Stead, Cory

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 12.00 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $250,541 |  |  |
| Total Cost: | $2,794,087 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 3,27100/2,408.51 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Drill, steer & survey 8½" hole from 3197m to 3271m. POOH to 1930m for BHA change (slow ROP). Held BOP drills. |
| Current: | POOH at 1930m. |
| Planned: | POOH to shoe. Slip & cut drill line. POOH & C/out BHA. RIH & drill to TD. |