DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 13, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 238 | 363 |
| --- | --- | --- |
| CAMERON | 1688 | 1688 |
| HALLIBURTON | 3475 | 3475 |
| SCHLUMBERGER | 2417 | 2417 |
| ISDL | 238 | 647 |
| ISS | 226 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 13, 2007

Supervisor:	Davis, Brian

Stead, Cory

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 13.00 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $230,984 |  |  |
| Total Cost: | $3,025,071 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 3,27100/2,408.51 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | POOH to shoe. Service rig. POOH to motor. Break out bit & M/U new bit. Function BOP's. RIH to3246m. Held BOP drills. |
| Current: | Washing & reaming at 3246m. |
| Planned: | Wash to 3271m. Drill to TD. Circulate hole clean. POOH. C/out MPR's to 4½" x 7" VBR's. POOH & L/out BHA. R/up & run 7" casing. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 14, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 239 | 363 |
| --- | --- | --- |
| CAMERON | 1688 | 1688 |
| HALLIBURTON | 3475 | 3475 |
| SCHLUMBERGER | 2417 | 2417 |
| ISDL | 239 | 647 |
| ISS | 227 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 14, 2007

Supervisor:	Stead, Cory

Steel, George A

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 14 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $249,146 |  |  |
| Total Cost: | $3,274,217 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 3,347.00/2,450.59 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Drill to TD of 3347m. Wiper trip to Top of Latrobe. POOH to 1920m. Held BOP drills. |
| Current: | POOH at 1920m. |
| Planned: | POOH to HWDP. C/out MPR's to 4½" x 7" VBR's. L/out BHA. Shell test stack. R/up & run 7" casing. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 15, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 240 | 363 |
| --- | --- | --- |
| CAMERON | 1688 | 1688 |
| HALLIBURTON | 3475 | 3475 |
| SCHLUMBERGER | 2417 | 2417 |
| ISDL | 240 | 647 |
| ISS | 228 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 15, 2007

Supervisor:	Davis, Brian

Stead, Cory

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 15 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $226,602 |  |  |
| Total Cost: | $3,500,819 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 3,347.00/2,450.59 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | POOH to 1623m. Circulate hole clean. POOH to HWDP. C/out MPR's to 7" casing rams. L/out BHA. Retrieve wear bushing. Jet wellhead & stack. Shell test BOP stack. Service rig. R/U & run 7" casing to 742m. Held BOP drills. |
| Current: | Running 7" casing at 742m. |
| Planned: | Run casing to 3342m. Circulate & condition mud. Cement & displace 7" casing. |