DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 16, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 241 | 363 |
| --- | --- | --- |
| CAMERON | 1688 | 1688 |
| HALLIBURTON | 3475 | 3475 |
| SCHLUMBERGER | 2417 | 2417 |
| ISDL | 241 | 647 |
| ISS | 229 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 16, 2007

Supervisor:	Stead, Cory

Steel, George A

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 16 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $227,685 |  |  |
| Total Cost: | $3,696,892 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 3,347.00/2,450.59 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Continue running 7" casing from 742m to 3342m. Circulate & condition mud. Mix, pump & place cement. Wait on cement. Held BOP drill. |
| Current: | Waiting on cement. |
| Planned: | Lift BOP's & set casing slips. Cut casing. N/dn BOP's. Dress casing & N/U tubing spool. N/U & test BOP's. |