DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 20, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 246 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 170 | 170 |
| CAMERON | 1721 | 1721 |
| HALLIBURTON | 3525 | 3525 |
| SCHLUMBERGER | 2430 | 2430 |
| ISS | 238 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 20, 2007

Supervisor:	Stead, Cory

Steel, George A

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 20 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $207,444 |  |  |
| Total Cost: | $4,944,380 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 3,347.00/2,450.59 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Remove wear bushing. Flush wellhead & BOP stack. R/U & run 2-7/8" tubing to 862m. Service rig. Cont. RIH w/ 2-7/8" tubing to 1942m. Held BOP drills. |
| Current: | RIH w/ 2-7/8" completion tubing at 1942m. |
| Planned: | RIH w/ 2-7/8" tubing to 3168.04m. Spaceout string, P/U landing jts & land out in hanger. Test seals & TRSSSV. Set packer. test tubing & PA. Set BPV. N/dn BOP's. N/U Xmas tree & THAF. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 21, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 247 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 171 | 171 |
| CAMERON | 1722 | 1722 |
| HALLIBURTON | 3526 | 3526 |
| SCHLUMBERGER | 2431 | 2431 |
| ISS | 239 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 21, 2007

Supervisor:	Stead, Cory

Steel, George A

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 21 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $755,007 |  |  |
| Total Cost: | $5,699,387 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 3,347.00/2,450.59 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Complete RIH & land 2-7/8" completion as per program. Test hanger seals. Function TRSSSV. R/U HES slickline & RIH w/ N-test tool. Pressure up tubing & set packers. POOH w/ N-test tool. Test upper & lower packer seals to 2000 psi. R/dn slickline, remove THRT & landing joints. Set BPV. N/dn bell nipple, flowline, BOP's & riser. Held trip drill. |
| Current: | Terminating control line. |
| Planned: | N/U xmas tree & pressure test. Pull BPV. R/U slickline & RIH w/ BO positioning tool. Open XD sliding sleeve. Hand well to Production Ops. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 22, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 248 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 172 | 172 |
| CAMERON | 1723 | 1723 |
| HALLIBURTON | 3527 | 3527 |
| SCHLUMBERGER | 2432 | 2432 |
| ISS | 240 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 22, 2007

Supervisor:	Stead, Cory

Steel, George A

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 21.5 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $309,762 |  |  |
| Total Cost: | $6,009,149 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 3,347.00/2,450.59 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Cameron terminate control line. Fit control line block to spool. N/U xmas tree. Test hanger seals to 5000 psi & test SRL seals to 800 psi. R/U wireline BOP & N/U on xmas tree. Remove BPV. R/U slickline. RIH w/ BO positioning tool & open SSD at 3106m. POOH & R/dn slickline. Install xmas tree cap & test. Hand well to Production Ops. Rig released to HLA A24 operations. |
| Current: | Rig released to HLA A24 operations. |
| Planned: | Rig released to HLA A24 operations. |