DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 6, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 231 | 363 |
| --- | --- | --- |
| CAMERON | 1686 | 1686 |
| HALLIBURTON | 3473 | 3473 |
| SCHLUMBERGER | 2415 | 2415 |
| ISDL | 231 | 647 |
| ISS | 219 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 6, 2007

Supervisor:	Stead, Cory

Davis, Brian

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 6.00 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $227,542 |  |  |
| Total Cost: | $1,349,862 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 2,369.00/1,801,35 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Drill, steer & survey 8½" hole from 1969m to 2369m. Held BOP drills. |
| Current: | Drlg 8.5" hole at 2369m |
| Planned: | Cont.Drlg 8.5" hole to 2900m, trip for LWD & tapered string |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 7, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 232 | 363 |
| --- | --- | --- |
| CAMERON | 1687 | 1687 |
| HALLIBURTON | 3474 | 3474 |
| SCHLUMBERGER | 2416 | 2416 |
| ISDL | 232 | 647 |
| ISS | 220 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 7, 2007

Supervisor:	Stead, Cory

Davis, Brian

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 7.00 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $232,895 |  |  |
| Total Cost: | $1,582,757 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 2,755.00/2,067.80 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Drill, steer & survey 8½" hole from 2369m to 2755m. Held BOP drills. |
| Current: | Drlg 8.5" hole at 2755m |
| Planned: | Cont.Drlg 8.5" hole to 2900m, trip for LWD & tapered string |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS JANUARY 8, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 233 | 363 |
| --- | --- | --- |
| CAMERON | 1688 | 1688 |
| HALLIBURTON | 3475 | 3475 |
| SCHLUMBERGER | 2417 | 2417 |
| ISDL | 233 | 647 |
| ISS | 221 | 2357 |

Well: HLA_A2B

Rig/Contractor: 	Rig 453	Report Date: January 8, 2007

Supervisor:	Stead, Cory

Davis, Brian

| AFE Number: AFE Number: | L0501G207 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 8.00 | AFE Cost/Days: | $5,677,031 |
| Daily Cost: | $219,403 |  |  |
| Total Cost: | $1,802,160 | Planned MD/TVD: | 3,299.00/3,058.68 |
| Casing Size: |  | Actual MD/TVD: | 2,930.00/2,188.91 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A2B |
| --- | --- |
| Management Summary: | Drill, steer & survey 8½" hole from 2755m to 2930m. Circulate hole clean. POOH from 2930m to 1010m. Held BOP drills. |
| Current: | POOH at 1010m. |
| Planned: | POOH & L/out BHA #1. M/U BHA #2, RIH & drill ahead to TD. |