DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS July 22, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 265 | 363 |
| --- | --- | --- |
| CAMERON | 5517 | 5530 |
| HALLIBURTON | 3339 | 3338 |
| SCHLUMBERGER | 2119 | 2118 |
| ISDL | 265 | 647 |
| ISS | 54 | 2355 |

Well: WKF_W27A

Rig/Contractor: 	Rig 453	Report Date: July 22, 2006

Supervisor:.	Davis, Brian

Stead, Cory

| AFE Number: | L0501G657 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 6.5 | AFE Cost/Days: | $5,800,000 |
| Daily Cost: | $187,050 |  |  |
| Total Cost: | $1,278,090 | Planned MD/TVD: | 3093.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2508.00/1947.38 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W27A |
| --- | --- |
| Management Summary: | Drill/slide/survey 8½" hole from 2415m to 2508m. POOH to inspect BHA - rapid pressure increase to 3600 psi. L/out Mud Motor. M/U BHA c/w new Mud Motor & shallow test. RIH to 785m. Slip & cut drill line. Service rig. C/out TDS saver |
| Current: | C/out TDS Saver Sub from 4" FH to 4½" IF. |
| Planned: | Circulate & condition mud. Stage in the hole to TD. Drill ahead. |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 266 | 363 |
| --- | --- | --- |
| CAMERON | 5518 | 5530 |
| HALLIBURTON | 3340 | 3339 |
| SCHLUMBERGER | 2120 | 2119 |
| ISDL | 266 | 647 |
| ISS | 55 | 2355 |

Well: WKF_W27A

Rig/Contractor: 	Rig 453	Report Date: July 23, 2006

Supervisor:.	Davis, Brian

Stead, Cory

| AFE Number: | L0501G657 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 7.5 | AFE Cost/Days: | $5,800,000 |
| Daily Cost: | $196,030 |  |  |
| Total Cost: | $1,474,120 | Planned MD/TVD: | 3093.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2716,00/2094.65 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W27A |
| --- | --- |
| Management Summary: | C/out TDS saver sub from 4" FH to 4½" IF. Stage in the hole on 4" DP to 2279m. RIH on 5" DP to 2508m. Circulate & condition mud. Drill/slide/survey 8½" hole from 2508m to 2716m. Service rig. Help BOP drills. |
| Current: | Drill/slide/survey 8½" hole at 2716m. |
| Planned: | Drill/slide/survey 8½" hole to TD. Wiper trip. POOH. |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 267 | 363 |
| --- | --- | --- |
| CAMERON | 5519 | 5530 |
| HALLIBURTON | 3341 | 3340 |
| SCHLUMBERGER | 2121 | 2120 |
| ISDL | 267 | 647 |
| ISS | 56 | 2355 |

Well: WKF_W27A

Rig/Contractor: 	Rig 453	Report Date: July 24, 2006

Supervisor:.	Davis, Brian

Stead, Cory

| AFE Number: | L0501G657 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 8.5 | AFE Cost/Days: | $5,800,000 |
| Daily Cost: | $207,359 |  |  |
| Total Cost: | $1,681,479 | Planned MD/TVD: | 3093.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 3081.00/2356.14 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W27A |
| --- | --- |
| Management Summary: | Drill 8½" Hole to 2768m. Circ hole clean. Drill 8½" hole to 3081m. Monitored KFA A-10a. Add Baracarb to the mud @ 2883m. Add EBL to mud @ 2969m. Held Pit Drills. |
| Current: | Drill & survey 8½" Production Hole at 3081m. |
| Planned: | Drill & Survey 8½" Hole to ~3093m. POOH & run logging assembly. |