DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS December 02, 2006

| RIG 453 | 197 | 363 |
| --- | --- | --- |
| CAMERON | 1672 | 1672 |
| HALLIBURTON | 3459 | 3459 |
| SCHLUMBERGER | 2401 | 2401 |
| ISDL | 197 | 647 |
| ISS | 185 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: December 02, 2006

Supervisor:	Campbell, Glenn R.

Brigham Bigby

| AFE Number: | LO501G206 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 31.0 | AFE Cost/Days: | $6,713,761 |
| Daily Cost: | $163,066 |  |  |
| Total Cost: | $5,276,822 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM & hazard hunts. Install monkey board mast section & monkey board ready for scoping. Dress out monkey board. WOW to scope mast - winds above scoping limits. Complete installing mud pump suction headers, pots & dampers. Continue to run mud pump suction lines. Assist electrician & Mechanic install cables & rig services. Rig Howco compressors into position on workshop roof. Mount possum belly. Install choke & kill lines. Arrange decks, unload equipment & prepare backloading. Run airlift hoses. General rig up operations ongoing. |
| Current: | Installing pump suction lines & airlift hoses. |
| Planned: | Continue general rig up operations. Scope mast when weather conditions permit. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS December 03, 2006

| RIG 453 | 198 | 363 |
| --- | --- | --- |
| CAMERON | 1673 | 1673 |
| HALLIBURTON | 3460 | 3460 |
| SCHLUMBERGER | 2402 | 2402 |
| ISDL | 198 | 647 |
| ISS | 186 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: December 03, 2006

Supervisor:	Campbell, Glenn R.

Brigham Bigby

| AFE Number: | LO501G206 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 32.0 | AFE Cost/Days: | $6,713,761 |
| Daily Cost: | $163,066 |  |  |
| Total Cost: | $5,439,888 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM & hazard hunts. WOW - crane shutdown with winds over 40 knot operating limit. Continue to run LP mud system lines. Assist Electrician & Mechanic install cables & rig services. Connect choke line at BOP's. Spot TDS on rig floor & secure in position. Dress BOP's. Arrange decks & prepare backloading. General rig up, housekeeping & maintenance operations ongoing. |
| Current: | Continue general rig up & fit mud system spools. |
| Planned: | Continue general rig up operations. Dress mast. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS December 04, 2006

| RIG 453 | 199 | 363 |
| --- | --- | --- |
| CAMERON | 1674 | 1674 |
| HALLIBURTON | 3461 | 3461 |
| SCHLUMBERGER | 2403 | 2403 |
| ISDL | 199 | 647 |
| ISS | 187 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: December 04, 2006

Supervisor:	Campbell, Glenn R.

Brigham Bigby

| AFE Number: | LO501G206 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 33.0 | AFE Cost/Days: | $6,713,761 |
| Daily Cost: | $163,066 |  |  |
| Total Cost: | $5,602,954 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM & hazard hunts. Continue to run LP mud system lines. Assist Electrician & Mechanic install cables & rig services. Arrange decks & prepare backloading. General rig up, housekeeping & maintenance operations ongoing. Install rig windwalls & wind deflectors. Dress mast. Install TDS torque beam. Install standpipe & standpipe guards. Spot landing on top of bulk pods. |
| Current: | Install standpipe guards. |
| Planned: | Install TDS service loop. Backspool drill line. Continue with general rig up operations. |