DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS November 11, 2006

| RIG 453 | 176 | 363 |
| --- | --- | --- |
| CAMERON | 1651 | 1651 |
| HALLIBURTON | 3438 | 3438 |
| SCHLUMBERGER | 2380 | 2380 |
| ISDL | 176 | 647 |
| ISS | 165 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: November 11, 2006

Supervisor:	Bennett, James

Davis, Brian

| AFE Number: | LO501G206 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 10.0 | AFE Cost/Days: | $6,713,761 |
| Daily Cost: | $163,066 |  |  |
| Total Cost: | $1,643,841 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | Conduct start of shift hazard hunts. Continue to rig down mud system spoolwork. Continue to pull back electrical cables and assist mechanic. Carry out scheduled crane service. Prepare BOP for shipment. Rig down strongbacks. Rig down Halliburton. Inspect all lifting equipment. Skid pipedeck clear of base tanks, skid active tanks clear of base tanks. Prepare brine tank for shipment to BBMT. Re-arrange main deck. |
| Current: | Rigging down and preparing loads for Boat #2 |
| Planned: | Move and position loads on HLA |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS November 12, 2006

| RIG 453 | 177 | 363 |
| --- | --- | --- |
| CAMERON | 1652 | 1652 |
| HALLIBURTON | 3439 | 3439 |
| SCHLUMBERGER | 2381 | 2381 |
| ISDL | 177 | 647 |
| ISS | 166 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: November 12, 2006

Supervisor:	Bennett, James

Davis, Brian

| AFE Number: | LO501G206 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 11.0 | AFE Cost/Days: | $6,713,761 |
| Daily Cost: | $163,066 |  |  |
| Total Cost: | $1,806,907 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | Conduct start of shift hazard hunts. Continue to rig down mud system spoolwork. Continue to pull back electrical cables and assist mechanic. Rig down strongbacks. Rig down Halliburton. Inspect all lifting equipment. Load strong backs, base & active tanks & stands. Rig skidding equipment. BOP stand. Safety & electrical container. |
| Current: | Loading Kady Kari-Ann. Boat Load #3 to HLA. |
| Planned: | Move and rig up on HLA |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS November 13, 2006

| RIG 453 | 178 | 363 |
| --- | --- | --- |
| CAMERON | 1653 | 1653 |
| HALLIBURTON | 3440 | 3440 |
| SCHLUMBERGER | 2382 | 2382 |
| ISDL | 178 | 647 |
| ISS | 167 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: November 13, 2006

Supervisor:	Bennett, James

Davis, Brian

| AFE Number: | LO501G206 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 12.0 | AFE Cost/Days: | $6,713,761 |
| Daily Cost: | $163,066 |  |  |
| Total Cost: | $1,969,973 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | Conduct start of shift hazard hunts. Load Boat #3 for HLA. Rig down Halliburton. Inspect all lifting equipment. Unload Boat #3 at HLA. Start building base tanks. Service Far Scandia, backload Halliburton cement unit, brine tank and surplus ISDL equipment. Start night shift on HLA and continue rigging up base tanks. Service Far Scandia on HLA, backload surplus construction equipment for BBMT. Dress and prepare to position top package strong backs. |
| Current: | Move and rig up on HLA. |
| Planned: | Rig up on HLA. |