DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS December 16, 2006

| RIG 453 | 211 | 363 |
| --- | --- | --- |
| CAMERON | 1680 | 1680 |
| HALLIBURTON | 3467 | 3467 |
| SCHLUMBERGER | 2409 | 2409 |
| ISDL | 211 | 647 |
| ISS | 199 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: December 16, 2006

Supervisor:	Bennett, James M

Steel, George A

| AFE Number: AFE Number: | L0501G204 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 1.0 | AFE Cost/Days: | $1,500,000 |
| Daily Cost: | $165,431 |  |  |
| Total Cost: | $165,431 | Planned MD/TVD: | 185.00/ |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. Prepare to skid rig to slot #12 ( HLA A24). Remove landings and walkways. Skid top package north. Reinstate landings and walkways. prepare bottom package to skid east. Skid bottom package to slot #12. Tie down rig and reinstate all landings, walkways and stairs. Tidy pipe deck and erect scaffold where needed. |
| Current: | Continue w/ rig up over slot #12. |
| Planned: | RIH w/ magnet assy. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS December 17, 2006

| RIG 453 | 212 | 363 |
| --- | --- | --- |
| CAMERON | 1681 | 1681 |
| HALLIBURTON | 3468 | 3468 |
| SCHLUMBERGER | 2410 | 2410 |
| ISDL | 212 | 647 |
| ISS | 200 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: December 17, 2006

Supervisor:	Bennett, James M

Steel, George A

| AFE Number: AFE Number: | L0501G204 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 2.0 | AFE Cost/Days: | $1,500,000 |
| Daily Cost: | $165,185 |  |  |
| Total Cost: | $330,616 | Planned MD/TVD: | 185.00/ |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. Conduct hazard hunt. M/up magnet assy and RIH to 171m. POOH and lay out BHA. No Junk. M/ cleanout assy and RIH to 171m. Drill/wash from 171m to 183m. POOH w/ cleanout BHA and M/up magnet assy. RIH w/ magnet BHA to 183m and POOH to surface. Recovered scaffold key. L/out BHA. R/up and RIH w/ 16" casing to 179m. Rig down weatherford and R/up to run iner string. M/up sealing adaptor and RIH w/ 5" HWDP to 116m. |
| Current: | RIH w/ inner string. |
| Planned: | Cement 16" casing. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS December 18, 2006

| RIG 453 | 213 | 363 |
| --- | --- | --- |
| CAMERON | 1682 | 1682 |
| HALLIBURTON | 3469 | 3469 |
| SCHLUMBERGER | 2411 | 2411 |
| ISDL | 213 | 647 |
| ISS | 201 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: December 18, 2006

Supervisor:	Bennett, James M

Steel, George A

| AFE Number: AFE Number: | L0501G204 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 3.0 | AFE Cost/Days: | $1,500,000 |
| Daily Cost: | $186,643 |  |  |
| Total Cost: | $517,259 | Planned MD/TVD: | 185.00/ |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM. Rig up cement head and secure casing. Cement 16" casing w/ 85 bbl of 15.9 ppg slurry. Bump dart w/ 2250 psi. POOH w/ stinger. WOC. Cut 16" casing and L/out. Break down cement head. Clear rig floor. Service Far Scandia. Rig service. P/up 4" drill pipe and rack back. |
| Current: | P/up 4" DP and rack back. |
| Planned: | Prepare to skid rig. |