DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 15, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 272 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 194 | 194 |
| CAMERON | 1747 | 1747 |
| HALLIBURTON | 3551 | 3551 |
| SCHLUMBERGER | 2456 | 2456 |
| ISS | 264 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: February 15, 2007

Supervisor:	Bareswill, JR (Dicky)

Campbell, Glenn R

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 22.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $248,318 |  |  |
| Total Cost: | $5,129,356 | Planned MD/TVD: | 2,984.99/2,616.57 |
| Casing Size: |  | Actual MD/TVD: | 2,991.00/2,452.97 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. Held trip & pit drills. Drill 8-1/2" production hole from 2960m to TD at 2991m. Circulate hole clean. Backream OOH from TD to 2721m - above TOL. Circulate hole clean. POH w/ 4" DP from 2721m to 619m - hole good. Circulate B/U - hole clean. POH w/ 4" DP from 619m to 211m & 5" HWDP from 211 to 38m. Recover radioactive logging source. Breakdown & layout BHA. |
| Current: | L/out drilling BHA & bit. |
| Planned: | C/out UPR's ready to rig up & run 7-inch casing. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 15, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 272 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 194 | 194 |
| CAMERON | 1747 | 1747 |
| HALLIBURTON | 3551 | 3551 |
| SCHLUMBERGER | 2456 | 2456 |
| ISS | 264 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 15, 2007

Supervisor:	Steel, George

Bennett, James

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 34.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $181,983 |  |  |
| Total Cost: | $5,902,155 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | PTSM's. Conduct Hazard hunt. Continue to install koomey hoses to rig floor. Prepare decks for boat. Install scaffolding and hand rails where needed. Commission / test hydraulic system. Test lift and roll system. Wire up and test drawworks. Install ducting to drawworks blowers. PSN Continue to fit light in HOWCO unit. Run cable in drilling office to rectify fire / gas operation. Prep for welding stubs and packing on DSM. Shorten bulk vent lines to raise above sea level. Sourcing 8" butterfly valve. Service Far Scandia. Remove monkey board, mast sections. Back load empty baskets / containers. Remove and install "A" legs mast sections. Boat departed to service HLA @ 18: 00hrs. Continue torque bolts on BOP's. Hang scoping slings on "A" legs. Remove TDS feet from "A" legs. Dress and prep crown section for lifting. Service Karri Ann whilst Install crown section. Rearrange pipe deck. Released Karri Ann. Service Far Scandia: unload remaining baskets / containers. Boat released @ 23: 15 hrs to BBMT. Hook up air lines to rig floor. Reeve blocks with drill line. Fill pits w/ sea water. Dress monkey board. Continue to hook up service hoses to rig floor. Held weekly safety meeting w/ night crew @ 06:30 hrs. Rig up 64% complete. |
| Current: | General rig up operations. |
| Planned: | Continue rig up. |