DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 21, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 278 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 200 | 200 |
| CAMERON | 1753 | 1753 |
| HALLIBURTON | 3557 | 3557 |
| SCHLUMBERGER | 2462 | 2462 |
| ISS | 270 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 21, 2007

Supervisor:	Steel, George

Bennett, James

Spence, Robert

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 40.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $181,983 |  |  |
| Total Cost: | $6,927,813 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Erect scaffold for electricians to terminate top drive service loop, install safety slings to service loops, complete positioning of rig air compressors, install drive belts on pulley 2 trip tank pump, commense installation of vent line from po-boy to mast. cont to secure hydraulic lines in mast. Hang rig tong counter weight lines and cut to suit. Install iron roughneck on to base on rig floor, drill and secure stairs on west side access to pipe deck. Dress fluid end on rig pumps. Held weekly safety meeting with day crew. Rig up 75% complete |
| Current: | General rig up operations |
| Planned: | Continue rig up |