DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 22, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 279 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 201 | 201 |
| CAMERON | 1754 | 1754 |
| HALLIBURTON | 3558 | 3558 |
| SCHLUMBERGER | 2463 | 2463 |
| ISS | 271 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 22, 2007

Supervisor:	Steel, George

Bennett, James

Spence, Robert

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 41.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $181,983 |  |  |
| Total Cost: | $7,109,796 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Cont. Rig up service looms on Top drive, Commision Fire and Generator shutdown. Backspool Drilling line from drawworks, Install "V" door rollar at A frame, and install Upper I-BOP on top drive shaft. Rig up 77% complete |
| Current: | General rig up operatons |
| Planned: | Continue rig up |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 22, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 279 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 201 | 201 |
| CAMERON | 1754 | 1754 |
| HALLIBURTON | 3558 | 3558 |
| SCHLUMBERGER | 2463 | 2463 |
| ISS | 271 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: February 22, 2007

Supervisor:	Bareswill, J R (Dicky)

Smith, Gary G

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 29.5 | AFE Cost/Days: | $7,818,363 |
| Daily Cost: | $208,329 |  |  |
| Total Cost: | $7,445,318 | Planned MD/TVD: | 2,985.00/2,616.58 |
| Casing Size: |  | Actual MD/TVD: | 2,991.01/2,452.98 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | N/u Bops, shell tested to 300/3000 psi, pressure testing RN plug and tubing to 2000 psi, Performed Packer Setting Pressure Schedule. Performed two Packer seal tests to 1500 psi for 15 min., 37 psi lost in 15 min. on both tests-Good Test. Pulled dummy valve at 140m, RIH to set LP-SC-SSSV at report time. |
| Current: | RIH to set 3.813" LP SC-SSSV at 140m |
| Planned: | Remove Bops-Install and test Tree. |