DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 14, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 286 | 363 |
| --- | --- | --- |
| CAMERON | 5539 | 5539 |
| HALLIBURTON | 3361 | 3360 |
| SCHLUMBERGER | 2141 | 21 |
| ISDL | 286 | 647 |
| ISS | 74 | 2364 |

Well: WKF_W21

Rig/Contractor: 	Rig 453	Report Date: August 12, 2006

Supervisor:	Campbell, Glen R

Davis, Brian

| AFE Number: | 40000458 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 4.2 | AFE Cost/Days: | $1,783,661 |
| Daily Cost: | $188,521 |  |  |
| Total Cost: | $769,239 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 2719.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21 |
| --- | --- |
| Management Summary: | L/dn 3½" Tbg. RIH w/ 4" DP. Tag HUD @ 2769.5m. Rig to & set cmt plug #1. POH t/ 2690m & rev circ. POH w/ 4" DP. L/dn 3½" tbg. RIH w/ 4" DP to HUD 2721m. Held Trip Drills. P/test well to 1000 psi. Displace to ISW. POH w/ 4" DP to 2312m. |
| Current: | POH to set cement plug #2. |
| Planned: | Lay down 3½" Tubing. N/Dn BOP. Remove Tubing Spool. N/up BOP. |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 287 | 363 |
| --- | --- | --- |
| CAMERON | 5540 | 5539 |
| HALLIBURTON | 3362 | 3361 |
| SCHLUMBERGER | 2142 | 21 |
| ISDL | 287 | 647 |
| ISS | 75 | 2364 |

Well: WKF_W21

Rig/Contractor: 	Rig 453	Report Date: August 13, 2006

Supervisor:	Campbell, Glen R

Davis, Brian

| AFE Number: | 40000458 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 5.2 | AFE Cost/Days: | $1,783,661 |
| Daily Cost: | $188,521 |  |  |
| Total Cost: | $769,239 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 757.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21 |
| --- | --- |
| Management Summary: | POH. Set Cmt plug #2 . Rev circ. L/dn 3½" tbg. R/dn WFD. N/dn BOP. N/dn tubing spool. Change rams to 7-5/8". N/up BOP's. BCFT. Shell test BOP/choke line. Held trip drills. Serviced work boat. P/up csg cutter BHA. RIH. Cut/circ csg. |
| Current: | Circulating cut casing with clean sea water. |
| Planned: | Layout 7-5/8" casing from ~753.5m. |

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 288 | 363 |
| --- | --- | --- |
| CAMERON | 5541 | 5540 |
| HALLIBURTON | 3363 | 3362 |
| SCHLUMBERGER | 2143 | 21 |
| ISDL | 288 | 647 |
| ISS | 76 | 2364 |

Well: WKF_W21

Rig/Contractor: 	Rig 453	Report Date: August 14, 2006

Supervisor:	Campbell, Glen R

Davis, Brian

| AFE Number: | 40000458 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 6.2 | AFE Cost/Days: | $1,783,661 |
| Daily Cost: | $188,521 |  |  |
| Total Cost: | $769,239 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 757.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21 |
| --- | --- |
| Management Summary: | Circ csg. POH & L/d cutter. L/o HWDP. BCFT. Held Trip Drills. M/u spear & latch csg. Close annular & circ csg. Recover slip & seal. L/o 7-5/8" csg. R/d WFD. L/o cutter & spear assy. Run W/bush. RIH w/ OEDP. Circ. Set cmt kickoff plug. |
| Current: | WOC. Monitor the well. |
| Planned: | WOC. Tag & Pressure Test plug/surface casing. POH to M/u drilling BHA. |