DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 26, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 300 | 363 |
| --- | --- | --- |
| CAMERON | 5553 | 5587 |
| HALLIBURTON | 3375 | 3374 |
| SCHLUMBERGER | 2155 | 24 |
| ISDL | 300 | 647 |
| ISS | 88 | 2367 |

Well: WKF_W21A

Rig/Contractor: 	Rig 453	Report Date: August 26, 2006

Supervisor:	Basset, Anthony A

Steel, George A

| AFE Number: | L0501G658 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 11.0 | AFE Cost/Days: | $5,120,000 |
| Daily Cost: | $179,836 |  |  |
| Total Cost: | $2,631,167 | Planned MD/TVD: | 2564.00/2403.00 |
| Casing Size: |  | Actual MD/TVD: | 2575.00/2412.60 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21A |
| --- | --- |
| Management Summary: | WOC. Lift BOP, set csg slips in 180 klbs tension. Cut csg, remove BOP/riser & dress csg stub. Install & p/test tbg spool. N/up riser/BOP & bell nipple/flow line. Begin 14 day BOP test. |
| Current: | Replace failed outer kill line valve. |
| Planned: | G/ring & junk basket run. Perf well, run scraper & run completion. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 27 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 301 | 363 |
| --- | --- | --- |
| CAMERON | 5554 | 5587 |
| HALLIBURTON | 3376 | 3375 |
| SCHLUMBERGER | 2156 | 24 |
| ISDL | 301 | 647 |
| ISS | 89 | 2367 |

Well: WKF_W21A

Rig/Contractor: 	Rig 453	Report Date: August 27, 2006

Supervisor:	Basset, Anthony A

Steel, George A

| AFE Number: | L0501G658 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 12.0 | AFE Cost/Days: | $5,120,000 |
| Daily Cost: | $22,422 |  |  |
| Total Cost: | $2,653,589 | Planned MD/TVD: | 2564.00/2403.00 |
| Casing Size: |  | Actual MD/TVD: | 2575.00/2412.60 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21A |
| --- | --- |
| Management Summary: | Rig service. Complete BOP p/testing. P/test 7" casing to 3000psi/15mins. **for following times see Completion report** |
| Current: | See WKF W-21a completion report. |
| Planned: | See WKF W-21a completion report. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 27 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 301 | 363 |
| --- | --- | --- |
| CAMERON | 5554 | 5587 |
| HALLIBURTON | 3376 | 3375 |
| SCHLUMBERGER | 2156 | 24 |
| ISDL | 301 | 647 |
| ISS | 89 | 2367 |

Well: WKF_W21A

Rig/Contractor: 	Rig 453	Report Date: August 27, 2006

Supervisor:	Basset, Anthony A

Steel, George A

| AFE Number: | L0501G658 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | .9 | AFE Cost/Days: | $5,120,000 |
| Daily Cost: | $156,460 |  |  |
| Total Cost: | $2,810,049 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 2544.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21A |
| --- | --- |
| Management Summary: | Set w/bushing. R/up Sch, run gauge ring to 2534m. POOH. Sch RIH 4½" HSD gun & perforate 2436m to 2437.5m. POOH spent gun. M/up 7" csg scraper & RIH to ??. Circ ISW. |
| Current: | Circulating inhibited s/water. |
| Planned: | Run 3½" tandem completion. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 28, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 302 | 363 |
| --- | --- | --- |
| CAMERON | 5555 | 5587 |
| HALLIBURTON | 3377 | 3376 |
| SCHLUMBERGER | 2157 | 24 |
| ISDL | 302 | 647 |
| ISS | 90 | 2367 |

Well: WKF_W21A

Rig/Contractor: 	Rig 453	Report Date: August 28, 2006

Supervisor:	Basset, Anthony A

Steel, George A

| AFE Number: | L0501G658 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 1.9 | AFE Cost/Days: | $5,120,000 |
| Daily Cost: | $172,574 |  |  |
| Total Cost: | $2,982,623 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 2544.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21A |
| --- | --- |
| Management Summary: | Circulate well to inhibited s/water. POOH 7" scraper. Pull w/bushing, jet wellhead. R/up WFD tong & equipment. RIH 3½" completion as per program from surface to 1870m. |
| Current: | RIH 3½" tandem completion @ 1870m. |
| Planned: | Complete RIH & land 3½" completion, N/down BOP, n/up tree. |