DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS September 01, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 106 | 363 |
| --- | --- | --- |
| CAMERON | 1581 | 1581 |
| HALLIBURTON | 3368 | 3368 |
| SCHLUMBERGER | 2319 | 2319 |
| ISDL | 106 | 647 |
| ISS | 95 | 2,328 |

Well: WKF_W21A

Rig/Contractor: 	Rig 453	Report Date: September 01, 2006

Supervisor:	Campbell, Glenn R

Steel, George A

| AFE Number: | 40000459 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 2.3 | AFE Cost/Days: | $1,576,600 |
| Daily Cost: | $190,226 |  |  |
| Total Cost: | $451,785 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 2952.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6, P&A |
| --- | --- |
| Management Summary: | M/up fishing tools. Unable to pass SPM's. Run blind box & scratcher to 1550m. Set DGLV @ 1478m KB. P/test tbg 1000psi/15mins. R/D w/line, set BPV. N/up BOP stack. Complete BOP p/testing. |
| Current: | Prepare to circulate bottoms up with ISW. |
| Planned: | Circ clean, pull 3½" to SSSV, RIH on 4" d/pipe. |