DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 14, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 271 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 193 | 193 |
| CAMERON | 1746 | 1746 |
| HALLIBURTON | 3550 | 3550 |
| SCHLUMBERGER | 2455 | 2455 |
| ISS | 263 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: February 14, 2007

Supervisor:	Bareswill, JR (Dicky)

Campbell, Glenn R

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 21.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $233,630 |  |  |
| Total Cost: | $4,881,038 | Planned MD/TVD: | 2,984.99/2,616.57 |
| Casing Size: |  | Actual MD/TVD: | 2,960.00/ |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. Held trip & pit drills. RIH w/ BHA on 4" DP from 211m to 619m. Slip & cut drill line. Rig service. RIH w/ BHA on 4" DP from 619m to 2809m. Precautionary wash & ream and relog last 2 stds to bottom with LWD tools. Drill 8-1/2" production hole from 2873m to 2960m. |
| Current: | Drill 8-1/2" production hole. |
| Planned: | Drill & survey 8-1/2" production hole to TD. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 14, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 271 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 193 | 193 |
| CAMERON | 1746 | 1746 |
| HALLIBURTON | 3550 | 3550 |
| SCHLUMBERGER | 2455 | 2455 |
| ISS | 263 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 14, 2007

Supervisor:	Steel, George

Bennett, James

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 33.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $181,983 |  |  |
| Total Cost: | $5,720,172 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | PTSM's Rig up to hang choke / kill hoses from manifold. Assist mechanic and electrician install power to drill floor. Complete installation of engine exhaust. Continue w/ spooling at shakers and pits. Install grating for auger system. Complete installation of de-gasser/de-sander lines. empty baskets/containers for back load to BBMT. Clear decks for boat. Install timbers and covers on pipe deck. Install cement hard line from cement unit to cement manifold on rig floor. Run BOP control lines from dog house to BOP. Held weekly safety meeting for day shift @ 18:30 hrs. Rig up 62% completed. |
| Current: | General rig up operations |
| Planned: | Continue w/ rig up. |