DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 8, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 265 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 187 | 187 |
| CAMERON | 1740 | 1740 |
| HALLIBURTON | 3544 | 3544 |
| SCHLUMBERGER | 2449 | 2449 |
| ISS | 257 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: February 8, 2007

Supervisor:	Bareswill, JR (Dicky)

Campbell, Glenn R

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 15.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $245,147 |  |  |
| Total Cost: | $3,410,131 | Planned MD/TVD: | 2,984.99/2,616.57 |
| Casing Size: |  | Actual MD/TVD: | 2,301.00/ |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. Held pit drills. Drill, steer & survey 8 1/2" production hole from 1875m to 2283m. Rig service. Drill, steer & survey 8 1/2" production hole from 2283m to 2301m. |
| Current: | Drill 8-1/2" production hole. |
| Planned: | Continue to drill, steer & survey 8-1/2" production hole. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 8, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 265 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 187 | 187 |
| CAMERON | 1740 | 1740 |
| HALLIBURTON | 3544 | 3544 |
| SCHLUMBERGER | 2449 | 2449 |
| ISS | 257 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 8, 2007

Supervisor:	Davis, Brian

Bennett, James

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 27.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $179,958 |  |  |
| Total Cost: | $4,615,674 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | PTSMs.Install choke & kill valves. Position choke & kill hoses in sub base. Commence installation of lift & roll system. Continue to install rig lighting. Empty baskets and containers. Continue w/ mud tank spooling. Install east rig floor section. Adjust drill floor rigging, position 2nd drill floor section and pin section together. Hook up rig floor drains. Service lady karri Ann w/ platform lifts. Hook up pipe sections in sub base. Prep for boat. Clear decks. Install drag chain basket. Construction commision fire/gas testing on outside quarters. Rig up 48% complete. Held weekly safety meeting w/ night crew. |
| Current: | General rig up operations. |
| Planned: | Continue rig up operations. |