DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 2, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 135 | 363 |
| --- | --- | --- |
| CAMERON | 1610 | 1610 |
| HALLIBURTON | 3398 | 3398 |
| SCHLUMBERGER | 2339 | 2339 |
| ISDL | 135 | 647 |
| ISS | 124 | 2340 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: September 30, 2006

Supervisor:	Bennett, James M.

Campbell, Glenn R.

Steel, George A.

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 23.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 253,254 |  |  |
| Total Cost: | $ 5,266,277 | Planned MD/TVD: | 3477.00/ |
| Casing Size: |  | Actual MD/TVD: | 3477.00/2371.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | POOH with 4" d/pipe. Change UPR’s to 7". R/up Sch, RIH perf gun & perf well. Change UPR’s to VBR’s, RIH with 7" scraper to 1321m. Trip drills. |
| Current: | RIH 7" scraper @ 1321m. |
| Planned: | Circ well to ISW, POOH. Run 3½" tandem completion. |

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 136 | 363 |
| --- | --- | --- |
| CAMERON | 1611 | 1611 |
| HALLIBURTON | 3399 | 3399 |
| SCHLUMBERGER | 2340 | 2340 |
| ISDL | 136 | 647 |
| ISS | 125 | 2341 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: October 1, 2006

Supervisor:	Bennett, James M.

Campbell, Glenn R.

Steel, George A.

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 24.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 185,608 |  |  |
| Total Cost: | $ 5,454,511 | Planned MD/TVD: | 3477.00/ |
| Casing Size: |  | Actual MD/TVD: | 3477.00/2371.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | RIH with 4" d/pipe to 3442m. Work scraper over packer depths & perfs. Displace well to ISW. POOH with 4" d/pipe. L/out 147 jnts – rack remainder. P/up 3½" completion assemblies & RIH to 282m. Trip drills. |
| Current: | RIH with 3½" completion @ 282m. |
| Planned: | Land completion, set packers, n/down BOP’s, n/up tree. |

| RIG 453 | 137 | 363 |
| --- | --- | --- |
| CAMERON | 1612 | 1612 |
| HALLIBURTON | 3400 | 3400 |
| SCHLUMBERGER | 2341 | 2341 |
| ISDL | 137 | 647 |
| ISS | 126 | 2342 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: October 2, 2006

Supervisor:	Bennett, James M.

Campbell, Glenn R.

Steel, George A.

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 25.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 725,374 |  |  |
| Total Cost: | $ 6,179,885 | Planned MD/TVD: | 3477.00/ |
| Casing Size: |  | Actual MD/TVD: | 3477.00/2371.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | RIH w/ 3½", 9.2lb/ft,13CR-80 Vam-Top completion as per program to 3338.5m. Pressure test hanger seals to 5000psi/10 mins. |
| Current: | R/up wireline to run N-test tool & set packers. |
| Planned: | Set packers & p/test, n/down BOP, n/up tree, open SSD. |