DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS September 14, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 119 | 363 |
| --- | --- | --- |
| CAMERON | 1592 | 1592 |
| HALLIBURTON | 3380 | 3380 |
| SCHLUMBERGER | 2330 | 2330 |
| ISDL | 119 | 647 |
| ISS | 108 | 2327 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: September 14, 2006

Supervisor:	Campbell, Glenn R

Davis, Brian

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 7.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 177,341 |  |  |
| Total Cost: | $ 1,649,105 | Planned MD/TVD: | 3477.00/2368.00 |
| Casing Size: |  | Actual MD/TVD: | 2769.00/1944.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | Press test BOP's. Run wear bushing. M/up bit & RIH to shoe. Change saver sub. Slip & Cut. Rig Service. Conduct trip drills. RIH. Stage in the hole, Circulate and wash to bottom as required. |
| Current: | TIH @ 2357m. Clean out tight hole as required. |
| Planned: | TIH. Clean out tight hole as required. Drill & Survey 8½" Hole. |