DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS September 21, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 126 | 363 |
| --- | --- | --- |
| CAMERON | 1601 | 1601 |
| HALLIBURTON | 3389 | 3389 |
| SCHLUMBERGER | 2330 | 2330 |
| ISDL | 126 | 647 |
| ISS | 115 | 2330 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: September 21, 2006

Supervisor:	Basset, Anthony A.

Bennett, James M.

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 14.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 185,615 |  |  |
| Total Cost: | $ 3,124,281 | Planned MD/TVD: | 3477.00/2368.00 |
| Casing Size: |  | Actual MD/TVD: | 3477.00/2371.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | RIH w/ cleanout BHA from 315m to 2800m. CBU @ 689m, 1400m, 2100m and 2800m. Observed pressure drop. POOH to 1808m, located washout, L/out damaged pipe. RIH from 1808 to 3477m. Pump sweep, Circ hole clean, POOH to 1795m. Trip drill. |
| Current: | POOH with wiper BHA @ 1795m. |
| Planned: | POOH and L/out wiper BHA. Run 7" production casing as per program. |