DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS September 25, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 128 | 363 |
| --- | --- | --- |
| CAMERON | 1603 | 1603 |
| HALLIBURTON | 3391 | 3391 |
| SCHLUMBERGER | 2332 | 2332 |
| ISDL | 128 | 647 |
| ISS | 117 | 2332 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: September 23, 2006

Supervisor:	Steele, George A.

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 16.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 180,527 |  |  |
| Total Cost: | $ 3,485,335 | Planned MD/TVD: | 3477.00/2368.00 |
| Casing Size: |  | Actual MD/TVD: | 3477.00/2371.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | Operations suspended due to platform fire pumps shut down. Reduce manning on WKF. Relocate 3rd Party Contractors to KFB. Monitor well whilst conduct maintenance on equipment. Circulate and condition mud every 6 hours. |
| Current: | Wait on fire pump maintenance. |
| Planned: | Wait on fire pump maintenance. Wiper trip. Run 7” casing. |

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 129 | 363 |
| --- | --- | --- |
| CAMERON | 1604 | 1604 |
| HALLIBURTON | 3392 | 3392 |
| SCHLUMBERGER | 2333 | 2333 |
| ISDL | 129 | 647 |
| ISS | 118 | 2334 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: September 24, 2006

Supervisor:	Bennett, James M.

Steel, George A.

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 17.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 175,883 |  |  |
| Total Cost: | $ 3,662,541 | Planned MD/TVD: | 3477.00/2368.00 |
| Casing Size: |  | Actual MD/TVD: | 3477.00/2371.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | Fire pump engine changed out with function of all systems complete & satisfactory. OK given to re-man platform & commence rig operations. RIH from casing shoe to 3477m w/ wiper trip BHA. Circulate hole clean @ 1600m, 2500m and 3477m. POOH from 3477m to 2670m. Trip drill. |
| Current: | POOH w/ cleanout BHA @ 2670m. |
| Planned: | POOH and L/out cleanout BHA. Run 7” casing. |

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 130 | 363 |
| --- | --- | --- |
| CAMERON | 1605 | 1605 |
| HALLIBURTON | 3393 | 3393 |
| SCHLUMBERGER | 2334 | 2334 |
| ISDL | 130 | 647 |
| ISS | 119 | 2335 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: September 25, 2006

Supervisor:	Bennett, James M.

Steel, George A.

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 18.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 174,400 |  |  |
| Total Cost: | $ 3,836,941 | Planned MD/TVD: | 3477.00/2368.00 |
| Casing Size: |  | Actual MD/TVD: | 3477.00/2371.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | POOH from 2670m to 695m. Circulate bottoms up. Winds expected to be in excess of 40kts. Monitor well on trip tank whilst waiting on weather. RIH to 3477m, TD whilst waiting on weather conditions to abate. Winds to 55+kts. Circulate hole clean. POOH to 980m. Trip drill. |
| Current: | POOH w/ cleanout BHA @ 980m. |
| Planned: | POOH and L/out w/ cleanout BHA. Run 7” casing. |