LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Wombat-4 | REPORT No. : | 12 | DFS: | 12 | DATE : | 28-10-9 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1378 | LAST DEPTH : | 1366 | 24 HR PROGRESS: | 12 | PTD : |  |
| TOTAL FUEL : | 6,700 | FUEL USAGE : | 1,300 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Change out Rams to 7" prior to running Casing |
| Next 24 Hrs Op | Run and Cement Casing |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 3 | 4RR |  | Drilling | 2.0 |  | Density | 1.267 | S.G. |
| Size (mm) | 216 | 216 |  | Tripping | 11.0 |  | Viscosity | 54 | Sec |
| Make | Reed | Reed |  | Surveys |  |  | Water Loss | 7.0 | Cc |
| Type | HD219 | TD43 |  | Wireline logging | 6.0 |  | pH | 8.5 | Strip |
| IADC Code | 2-1-7 | 4-37 |  | Testing/tools |  |  | Filter Cake | 2 | 32 nd |
| Serial Number | AO8438 | W73458 |  | Circulate Sample | 1.0 |  | PV / YP | 18 / 35 | Cp/lb/100’ |
| Nozzles (32) | 14-14-14 | 14-14-14 |  | Casing |  |  | Gels | 7 / 10 | S/m |
| Depth in (m) | 1184 | 1366 |  | Cementing |  |  | Sand | 0.70 | % Vol |
| Depth out (m) | 1366 | 1378 |  | Surveys |  |  | Solids | 11.6 | % Vol |
| Total Metres | 182 | 12 |  | Circulate & Condition | 1.5 |  | Oil |  | % Vol |
| Hours | 40 | 2 |  | Rig Service/slip & cut | 0.5 |  | K+ | 11,550 | Mg/l |
| WOB (kg) | 9,000 | 7,000 |  | Rig down bop |  |  | Chlorides | 18,000 | Mg/l |
| RPM | 100 | 100 |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | 8-8-WT –A-E-1/8-ER-PR |  |  | Reaming | 1.5 |  | KCL | 2.2 | % |
| Impact Force | 415 |  |  | Wait On Cement |  |  | Daily Cost $ | 2,001 |
| Jet Velocity | 234 |  |  | Test BOPs |  |  | Cum Cost $ | 29,999 |
| B.H.A.: | BHA # 3 216mm Bit –Bit Sub-NMDC-1 x 6¼" DC-8½"Stab-7 x 6¼" Drill Collars-Drilling Jar-3 x 6¼"Drill Collars-4 x HWDP-Crossover sub |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 1½º N60E | ° at | 1354 | m |  | Type | Amount |
| 0000 | 04.30 | Continued to trip out with Bit # 3 |  |  | ° at |  | m |  | AMC Biocide G | 1 |
| 04.30 | 10.30 | Rig up Schlumberger ran logs |  |  | ° at |  | m |  | Caustic | 1 |
| 10.30 | 11.30 | Made up Bit # 4 tripped in hole to 179m |  |  | ° at |  | m |  | Pac - R | 1 |
| 11.30 | 12.00 | Serviced the Rig |  |  | ° at |  | m |  | Barite | 56 |
| 12.00 | 12.30 | Tripped in hole to 419m |  |  | ° at |  | m |  | Potassium Chloride | 45 |
| 12.30 | 13.00 | Filled pipe |  |  | ° at |  | m |  |  |  |
| 13.00 | 15.30 | Tripped in hole to 1335m |  |  | ° at |  | m |  |  |  |
| 15.30 | 17.00 | Picked up Kelly washed and light reamed to bottom |  |  |  |  |
| 17.00 | 19.00 | Drilled 216mm hole from 1366m to 1378 m |  | PUMP 1 Duplex |  | PUMP 2 Triplex |
| 19.00 | 20.00 | Circulated bottoms up sample |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 20.00 | 20.30 | Slugged pipe |  | Pressure | 7,200 | kPa |  | Pressure |  | KPa |
| 20.30 | 24.00 | Tripped out for Casing to 159m |  | A.V. DP | 40 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 70 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 52 |  | SPM |  |
|  |  |  |  | LPM | 325 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 9⅝" | inch |
|  |  |  |  | Class Bulk |  |  | Weight | 36 | ppf |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  | Held BOP Drill |  | % |  |  |  | Joints | 25 |  |
|  |  |  |  | % |  |  |  | Length |  | m |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 299m from RKB | m |

,66