LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Wombat-4 | REPORT No. : | 29 | DFS: | 29 | DATE : | 14-11-09 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 2,500 | LAST DEPTH : | 2,500 | 24 HR PROGRESS: |  | PTD : | Total Depth |
| TOTAL FUEL : | 2,300 | FUEL USAGE : | 1,200 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Recovering Schlumberger core samples |
| Next 24 Hrs Op | Run DST |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES @ 22.30 |
| --- | --- | --- | --- | --- |
| Bit Number | 5 Re-Run#4 | 6 New |  | Drilling |  |  | Density | 1.297 | S.G. |
| Size (mm) | 156 | 156 |  | Tripping | 8.5 |  | Viscosity | 42 | Sec |
| Make | Smith | Reed |  | Downtime ( Float ) |  |  | Water Loss | 14.0 | Cc |
| Type | MDi613 | R22AP |  | Wireline logging | 15.5 |  | pH | 8.0 | Strip |
| IADC Code |  | 5-1-7 |  | Testing/tools |  |  | Filter Cake | 4 | 32 nd |
| Serial Number | JD1042 | KD1019 |  | Circulate Sample |  |  | PV / YP | 16/19 | Cp/lb/100’ |
| Nozzles (32) | 3 x 12 | 3 x 14 |  | Casing |  |  | Gels | 5 / 16 | S/m |
| Depth in (m) | 1378 / 1478 | 2403 |  | Cementing |  |  | Sand | 0.50 | % Vol |
| Depth out (m) | / 2403 | 2500 |  | Surveys |  |  | Solids | 14.6 | % Vol |
| Total Metres | 1025 | 97 |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 123 | 38.5 |  | Rig Service/slip & cut |  |  | K+ | 36,750 | Mg/l |
| WOB (kg) | 2,000/5000 | 10-18k |  | Rig up/ d own bop |  |  | Chlorides | 45,000 | Mg/l |
| RPM | 90 /100 | 90 |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | 1-2-ER-A-X-2mm-NO-HRS | 3-3-ER-A-E-1-TD |  | Reaming |  |  | KCL | 7.0 | % |
| Impact Force | 237 | 176 |  | Wait On Cement |  |  | Daily Cost $ | 7,283 |
| Jet Velocity | 215 | 158 |  | Test BOPs |  |  | Cum Cost $ | 82,281 |
| B.H.A.: 5 | 156mm Bit-NBS-NMDC-1 x DC-STB-13 x DC-Jars-2 xDC |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 1½º N60E | ° at | 1354 | m |  | Type | Amount |
| 0000 | 02.00 | Continued trip in hole to 2500m no fill or resistance |  | 4ºN340W | ° at | 1768 | m |  | AMC Pac L |  |
| 02.00 | 06.30 | Circulated and conditioned mud properties ( Mud Wt ) |  | 12ºN340W | ° at | 2093 | m |  | AMC Pac R |  |
| 06.30 | 13.00 | Tripped out for logging re-run |  | 18.5 | ° at | 2235 | m |  | Lakes Pac R |  |
| 13.00 | 16.00 | Rigged up Schlumberger-safety meeting-Ran sonic tool |  | N340W | ° at |  | m |  | Xan Bore | 7 sx |
| 16.00 | 17.00 | Worked stuck tools free at 2,000m |  |  | ° at |  | m |  | Bayrtes | 513 |
| 17.00 | 20.00 | Continued logging after freeing tools-pulled tools |  |  | ° at |  | m |  | Potassium Chloride |  |
| 20.00 | 24.00 | Ran MSCT log |  |  | ° at |  | m |  | AMC Biocide G |  |
|  |  |  |  | PUMP 1 Duplex |  | PUMP 2 Triplex |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure |  | kPa |  | Pressure | 4,300 | KPa |
|  |  |  |  | A.V. DP |  | f/min |  | A.V. DP | 215 | Ft/min |
|  |  |  |  | A.V. DC |  | f/min |  | A.V. DC | 364 | Ft//mn |
|  |  |  |  | SPM |  |  | SPM | 100 |
|  |  |  |  | GPM |  |  | GPM | 225 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 7" | inch |
|  |  | Hunt 16 camp 4 |  | Class Bulk |  |  | Weight | 26 | ppf |
|  |  | Lakes 4 |  | % |  |  |  | Grade | K-55 |  |
|  |  | Mud logger 2 |  | % |  |  |  | Connection | BTC |  |
|  |  | Farley Riggs 4 |  | % |  |  |  | Joints | 117 |  |
|  |  | RMN 1 |  | % |  |  |  | Length | RT-Brd Hd 5.0 | m |
| Days since | LTA | Schlumberger 6 |  | Av. Wt |  |  | Shoe | 1376m from RKB | m |

,66